Section 8 - Particular Conditions of Contract

The following Particular Conditions of Contract (PCC) shall supplement the General Conditions of Contract (GCC). Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

Part A – Contract Data

| ### Ref. GCC | Subject | Data |
| --- | --- | --- |
| 1.1.2.2 and 1.3 | Employer’s name and address | TWAD Board, No. 30, Siruvani Nagar, Bharathipark Road, City: Coimbatore ZIP code: 641 043 Country: India |
| 1.1.2.4 and 1.3 | Engineer’s name and address | To be included before contract signing |
| 1.1.2.11 | Bank’s name | Asian Development Bank (ADB) |
| 1.1.2.12 | Borrower’s name | India |
| 1.1.3.3 | Time for Completion | Construction Activity: 42 Months |
| 1.1.3.7 | Operation Service Period | 1825 days(5 years) |
| 1.1.5.6 | Sections | Not applicable |
| 1.3 | Electronic transmission systems | By E-mail |
| 1.4 | Governing Law | The law of Borrower’s country. |
| 1.4 | Ruling language | English |
| 1.4 | Language for communications | English |
| 2.1 | Time for access to the Site | “14 days after Commencement Date” |

| 3.1(B)(ii) | Engineer’s Duties and Authority | Variations resulting in an increase of the Accepted Contract Amount in excess of 1.0% shall require approval of the Employer. |
| --- | --- | --- |
| 4.2 | Performance Security | The performance security will be in the form of an unconditional bank guarantee in the amount(s) of: 5% of the Contract price, subject to ITB 36.5. If the Bank issuing the Security is located outside India, it shall have a correspondent Bank located in the territory of India to make it enforceable. Following 36.5 If the employer determines that the lowest evaluated bid price is seriously unbalanced or front loaded the Employer at its discretion, may increase the Performance Security to a level sufficient to protect it against financial loss. |
| 6.5 | Normal working hours | Eight hours |
| 6.25 | Respectful Work Environment | The following sentence shall apply: The Contractor shall ensure that its employees and Subcontractors observe the highest ethical standards and refrain from any form of bullying, discrimination, misconduct and harassment, including sexual harassment and shall, at all times, behave in a manner that creates an environment free of unethical behavior, bullying, misconduct and harassment, including sexual harassment. The Contractor shall take appropriate action against any employees or subcontractors, including suspension or termination of employment or subcontract, if any form of unethical or inappropriate behavior is identified. The Contractor shall conduct training programs for its employees and Subcontractors to raise awareness on and prevent any form of bullying, discrimination, misconduct and harassment including sexual harassment, and to promote a respectful work environment. The Contractor shall keep an up-to-date record of its employees and Subcontractors who have attended and completed such training programs and provide such records to the Employer or the Engineer at their first written request. |
| 8.7 & 14.15(b) | Delay damages for the Works | 0.05% of the Contract Price per day, in the currencies and proportions in which the Contract Price is payable. |
| 8.7 | Maximum amount of delay damages | 10% of the Contract Price. |
| 10A.5(a) | Maximum compensation payable by Contractor: | 2% of the Contract Price. |
| 10A.5(b) | Maximum compensation payable by Employer: | 2% of the Contract Price. |
| 13.5.(b)(ii) | Provisional Sums | 5% |
| 13.8 | Adjustments for Changes in Cost | The Contract Price shall be adjustable during Contract Execution. |
| 14.1 | The Contract Price | The following sentence under Clause 14.1 shall not apply: “Notwithstanding the provisions of sub-paragraph (b), Contractor’s Equipment, including essential spare parts therefor, imported by the Contractor for the sole purpose of executing the Contract shall be exempt from the payment of import duties and taxes upon importation.” |
| 14.2 | Total advance payment | 10% Percentage of the Accepted Contract Amount payable in the currencies and proportions in which the Accepted Contract Amount is payable. |
| 14.2(b) | Repayment amortization of advance payment | 15% |
| 14.3(c) | Percentage of Retention | 5% |
| 14.3(c) | Limit of Retention Money | 5% of the Accepted Contract Amount. |
| 14.5(b)(i) | Plant and Materials | Subclause 14.5(b)(i) shall not apply |
| 14.5(c)(i) |  | Subclause 14.5(c)(i) shall not apply |
| 14.6 | Minimum Amount of Interim Payment Certificates | 0.25% of the Accepted Contract Amount. |
| 15.2 | Termination by Employer | This sentence will apply as Subclause 15.2(g): (g) the Engineer gives two consecutive Notices to update the Program and accelerate the works to ensure compliance with Subclause 8.2 (Time for Completion) and the Contractor fails to update the Program and demonstrate acceleration of the works within a reasonable period of time determined by the Engineer; |
| 15.6 | Corrupt and Fraudulent Practices | The following sentence shall apply: For the purposes of this Subclause: ADB’s Anticorruption Policy (1998, as amended to date)requires Borrowers (including beneficiaries of ADB-financed activity), as well as Contractors, Subcontractors, manufacturers, and Consultants under ADB-financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, ADB - defines, for the purposes of this provision, the terms set forth below as follows: #### “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; #### “fraudulent practice” means any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; #### “coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; #### “collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party; #### “abuse” means theft, waste, or improper use of assets related to ADB-related activity, either committed intentionally or through reckless disregard; #### “conflict of interest” means any situation in which a party has interests that could improperly influence that party’s performance of official duties or responsibilities, contractual obligations, or compliance with applicable laws and regulations; #### “obstructive practice” means (a) deliberately destroying, falsifying, altering, or concealing of evidence material to an ADB investigation, or deliberately making false statements to investigators, with the intent to impede an ADB investigation; (b) threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to a Bank investigation or from pursuing the investigation; or (c) deliberate acts intended to impede the exercise of ADB’s contractual rights of audit or inspection or access to information; and #### “integrity violation" is any act, as defined under ADB’s Integrity Principles and Guidelines (2015, as amended from time to time), which violates ADB’s Anticorruption Policy, including (i) to (vii) above and the following: violations of ADB sanctions, retaliation against whistleblowers or witnesses, and other violations of ADB's Anticorruption Policy, including failure to adhere to the highest ethical standard. - will reject a proposal for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations in competing for the Contract; - will cancel the portion of the financing allocated to a contract if it determines at any time that representatives of the borrower or of a beneficiary of ADB-financing engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations during the procurement or the execution of that contract, without the borrower having taken timely and appropriate action satisfactory to ADB to remedy the situation; and - will impose remedial actions on a firm or an individual, at any time, in accordance with ADB’s Anticorruption Policy and Integrity Principles and Guidelines, including declaring ineligible, either indefinitely or for a stated period of time, to participate in ADB-financed, -administered, or -supported activities or to benefit from an ADB-financed, -administered, or -supported contract, financially or otherwise, if it at any time determines that the firm or individual has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations. All Bidders, consultants, contractors, suppliers and other third parties engaged or involved in ADB-related activities have a duty to cooperate fully in any screening or investigation when requested by ADB to do so. Such cooperation includes, but is not limited to, the following: - being available to be interviewed and replying fully and truthfully to all questions asked; - providing ADB with any items requested that are within the party’s control including, but not limited to, documents and other physical objects; - upon written request by ADB, authorizing other related entities to release directly to ADB such information that is specifically and materially related, directly or indirectly, to the said entities or issues which are the subject of the investigation; - cooperating with all reasonable requests to search or physically inspect their person and/or work areas, including files, electronic databases, and personal property used on ADB activities, or that utilizes ADB’s Information and Communications Technology (ICT) resources or systems (including mobile phones, personal electronic devices, and electronic storage devices such as external disk drives); - cooperating in any testing requested by ADB, including but not limited to, fingerprint identification, handwriting analysis, and physical examination and analysis; and - preserving and protecting confidentiality of all information discussed with, and as required by, ADB. - All Bidders, consultants, contractors and suppliers shall ensure that, in its contract with its sub-consultants, Subcontractors, and other third parties engaged or involved in ADB-related activities, such sub-consultants, Subcontractors, and other third parties similarly undertake the foregoing duty to cooperate fully in any screening or investigation when requested by ADB to do so. |
| 17.6 | Maximum total liability of the Contractor to the Employer | The product of 1.1 times the Accepted Contract Amount. |
| 18.1 | Periods for submission of insurance: a. evidence of insurance. b. relevant policies | 14 days 28 days |
| 18.2(d) | Maximum amount of deductibles for insurance of the Employer's risks | Not applicable |
| 18.3 | Minimum amount of third party insurance | INR 1,00,00,000 (for 5 occurrence each of INR 20,00,000) |
| 18.5(a) | Amount of fire extended cover insurance | INR 1,00,00,000 |
| 18.5(b) | Minimum amount of professional liability | INR 10,00,000 |
| 18.5(b) | Period during which professional liability insurance is to be maintained by the Contractor | 5 years after the issue of the Commissioning Certificate. |
| 18.5(c) | Other insurances required by Laws or local practice from the Contractor | For Contractor’s workers 100% insurance cover shall be made in accordance with statutory requirements applicable in India |
| 20.2 | Date by which the Dispute Board shall be appointed | 28 days after the Commencement. |
| 20.2 | The Dispute Board shall be comprised of | One sole Member |
| 20.2 | List of potential Dispute Board sole members | To be agreed between “The Employer and the Contractor”. |
| 20.3 | Appointment (if not agreed) to be made by | The Institution of Engineers (India), Tamil Nadu Chapter. |
| 20.6 | Arbitration | For a Contractor registered or incorporated in India: (i) administered by the Chairman, Institution of Engineers, Tamil Nadu Chapter (ii) conducted in accordance with The Arbitration and Conciliation (Amendment) Act 2019, Government of India For a Contractor registered or incorporated outside India: (i) administered by: Singapore International Arbitration Centre (SIAC) (ii) conducted in accordance with the SIAC Rules 2016 |
| 20.6 | Place of Arbitration | For Contractor registered or incorporated in India: Chennai, State of Tamil Nadu, India For Contractor registered or incorporated outside India: Singapore |

- Part B – Specific Provisions

- Note -

Part B - Specific Provisions of the Particular Conditions of Contract are intended to address country, project, and contract specific requirements not covered by the General Conditions of Contract. Whoever drafts the specific provisions should be thoroughly familiar with the provisions of the General Conditions of Contract and with any specific requirements of the contract. Legal advice is recommended when amending provisions or drafting new ones.

| Sub-Clause No. in GCC | Sub-Clause title | Sub-clause contents |
| --- | --- | --- |
| CLAUSE 1 – GENERAL PROVISIONS |  |  |
| 1.1.2.7 | Contractor’s Personnel | After “execution of the Works”, add “and provision of the Operation Service.” |
| 1.1.3.7 | Operation Service Period | Replace that Sub-Clause entirely with the following: “Operation Service Period” means the period from the date stated in the Commissioning Certificate, as provided for under Sub-Clause 10A.2, [Commencement of Operation Service], and which extends over the number of days stated in the Contract Data (with any extension under Sub-Clause 11.3 [Extension of Operation Service Period]) |
| 1.1.4.1 | Accepted Contract Amount | Replace that Sub-Clause entirely with the following: “Accepted Contract Amount” means the amount accepted in the Letter of Acceptance for the execution and completion of the Works, the remedying of any defects and the provision of the Operation Service. |
| 1.1.6.11 | Operation and Maintenance Plan | Add the following new Sub-Clause: "Operation and Maintenance Plan" means the plan for operating and maintaining the Works, submitted by the Contractor and agreed by the Engineer in accordance with Sub-Clause 10A.1 [General Requirements]. |
| 1.1.6.12 | Operation Service | Add the following new Sub-Clause: “Operation Service” means the operation and maintenance of the Works as set out in the Specification. |
| 1.2 | Interpretation | Add the following sub-paragraphs, after sub-paragraph (e): “(f) any reference in these Conditions to “Taking-Over Certificate” shall be read as a reference to “Commissioning Certificate”, any reference to “taking over” shall be read as a reference to “commissioning”; and any reference to “taken over” shall be read as reference to “commissioned” (except in Sub-Clause 1.8 [Care and Supply of Documents]); and (g) any reference in these Conditions to “Defects Notification Period” shall be read as a reference to “Operation Service Period.” |
| 1.13 | Compliance with Laws | In the sub-paragraph (a) of this Sub-Clause, after “Permanent Works” add “and for the Operation Service”. In the sub-paragraph (b) of this Sub-Clause, after “execution and completion of the Works” add “and Operation Service”. |
| CLAUSE 3 – THE ENGINEER |  |  |
| 3.2 | Delegation by the Engineer | In the first paragraph of this Sub-Clause, after “Plant and/or Materials” add “and/or workmanship or monitor the provision of the Operation Service.”. Replace sub-paragraph (a) of this Sub-Clause, in its entirety by the following: “(a) any failure to disapprove any work, Plant, Materials or any part of the Operation Service shall not constitute approval, and shall therefore not prejudice the right of the Engineer to reject the work, Plant, Materials or any part of the Operation Service; and” |
| CLAUSE 4 – THE CONTRACTOR |  |  |
| 4.1 | Contractor’s General Obligations | Replace the first paragraph of this Sub-Clause in its entirety by the following: “The Contractor shall design (to the extent specified in the Contract), execute and complete the Works and provide the Operation Service in accordance with the Contract and shall remedy any defects in the Works. The Contractor shall provide the Plant and Contractor's Documents specified in the Contract, and all Contractor's Personnel, Goods, consumables and other things and services, whether of a temporary or permanent nature, required to meet the Contractor's obligations under the Contract.” Replace sub-paragraph (c) of this Sub-Clause in its entirety by the following: “(c) the Contractor shall be responsible for this part and it shall, when the Works are completed and during the whole Operation Service Period, be fit for such purposes for which the part is intended as are specified in the Contract; and” |
| 4.2 | Performance Security | Replace the third paragraph of this Sub-Clause in its entirety by the following: “The Contractor shall ensure that the Performance Security is valid and enforceable until the issue of the Performance Certificate. If the terms of the Performance Security specify its expiry date, and the Contractor has not become entitled to receive the Performance Certificate by the date 28 days prior to the expiry date, the Contractor shall extend the validity of the Performance Security until the Works and the Operation Service have been completed and any defects have been remedied.” Replace the sixth paragraph of this Sub-Clause in its entirety by the following: The Employer shall return the component of the Performance Security equivalent to five percent (5%) of the Accepted Contract Amount for the Works, except payment for Operation and Maintenance portion to the Contractor within 365 days after receiving a copy of the Commissioning Certificate. The Employer shall return the residual Performance Security to the Contractor within 21 days after receiving copy of the Performance Certificate. |
| 4.3 | Contractor’s Representative | In the fourth paragraph of this Sub-Clause, after “during the execution of the Works” add “or provision of the Operation Service” |
| 4.8 | Safety Procedures | After bullet point (b), add the following: The Contractor is responsible for providing site workers with safe and healthy working conditions and establish an operating system to prevent accidents, injuries, and disease, and report to the employer. Replace sub-paragraph (d) of this Sub-Clause in its entirety by the following: “(d) provide fencing, lighting, guarding and watching of the Works until the issue of the Performance Certificate; and” |
| 4.9 | Quality Assurance | In the second paragraph of this Sub-Clause, replace “and execution stage” by “, execution stage and operation stage”. |
| 4.10 | Site Data | In the second paragraph of this Sub-Clause, replace “Tender or Works” by “Tender or Works or provision of the Operation Service.” |
| 4.11 | Sufficiency of the Accepted Contract Amount | In the second paragraph of this Sub-Clause, after “remedying of any defects”, add: “and the provision of the Operation Service.” |
| 4.13 | Rights of Way and Facilities | Insert the following at the end of this clause: “The Contractor shall comply with (i) the measures and requirements relevant to the Contractor which are set forth in the Resettlement Plan (“RP”) attached hereto as Appendix [1_], to the extent it concerns impacts on affected people during construction; and (ii) any corrective or preventive actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor implementation of the resettlement plan. The Contractor shall allocate a budget for compliance with these measures, requirements and actions.” |
| 4.16 | Transport of Goods | In the sub-paragraph (b) of this Sub-Clause, replace “required for the Works” by: “required for the Works or provision of the Operation Service.” |
| 4.17 | Contractor’s Equipment | In this Sub-Clause, replace “execution of the Works” by “execution of the Works or the provision of the Operation Service”. |
| 4.18 | Protection of the Environment | At the end of the sub-clause in 4.18 Protection of the Environment, add the following paragraphs: “Without prejudice to any other obligation under or in connection with the Contract, the Contractor shall comply with all environmental requirements stated in the Employer’s Requirements, and in particular with those which may be set forth in the initial environmental examination and environmental management plan, as well as in any safeguards monitoring report of the project which may be included in the Employer’s Requirements.” “The Contractor shall comply with all applicable national, provincial, and local environmental laws and regulations. The Contractor shall also comply with all reasonable requests of the national and local authorities responsible for enforcing environmental controls. Within 28 days of the Commencement Date the Contractor shall submit a detailed Site Specific Environmental Management Plan (SSEMP) for the Engineer’s no objection showing how he/she intends to comply with environmental laws and regulations and other specific requirements prescribed in the Contract, addressing all the monitoring and mitigation measures set forth in the Environmental Impact Assessment (“EIA”) and the Environmental Management Plan (“EMP”) of the project attached in Section 6- Employer’s Requirements. Work shall not commence on the Site until the no objection of SSEMP has been obtained from the Engineer and is being implemented. Such acceptance by the Engineer shall not relive the Contractor of any of his obligations or responsibilities under the Contract. The Contractor shall (a) establish an operational system for managing environmental impacts, (b) comply with the approved SSEMP and any corrective or preventative actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor the implementation of the project EMP through the SSEMP, (c) allocate the budget required to ensure that such measures, requirements and actions are carried out, (d) submit semi-annual reports on the compliance of such measures to the Employer. Where unanticipated environmental risks or impacts become apparent during the Contract, the Contractor is required to update the SSEMP to outline the potential impacts to site works and associated mitigation measures for the Engineer’s approval.” |
| 4.19 | Electricity, Water and Gas | In the first paragraph of this Sub-Clause, after “for the tests”, add: “and the Operation Service.” |
| 4.21 | Progress Reports | Replace the second paragraph, and the first sentence of the third paragraph of this Sub-Clause, in their entirety by the following: “Reporting on progress shall continue until the Contractor has received the Performance Certificate. Details of the content of the progress reports for the Operation Service Period shall be as specified in the Specification. Unless otherwise stated or agreed, each progress report shall include: - charts and detailed descriptions of progress, including each stage of design, Contractor's Documents, procurement, manufacture, delivery to Site, construction or replacement, erection, testing, commissioning, trial operation and provision of Operation Service;” |
| CLAUSE 6 – STAFF AND LABOUR |  |  |
| 6.5 | Working Hours | Add the following sub-paragraph(d) after sub-paragraph(c): “(d) required for the proper fulfilment of the requirements of the Operation Service.” |
| 6.6 | Facilities for Staff and Labour | Add following paragraphs at the end of this sub-clause: The labor camp should be constructed following the standards outlined in the IFC and EBRD Accommodation Guidance Note [(can be found in this link: Workers' Accommodation: Processes and Standards (ifc.org)], including hygienic facilities with proper ablution facilities, waste management. No camp facilities should be located within areas considered at risk of flooding or natural hazards. |
| 6.7 | Health and Safety | After the first paragraph, add the following: The contractor is responsible for establishment of preventive and emergency preparedness and response measures to avoid, and where avoidance is not possible, to minimize, adverse impacts and risks of the construction site work to the health and safety of local communities. Within 28 days of the commencement date the contractor shall submit a detailed site specific health and safety management plan (SSHSMP), including HS-C19 Plan, for the employer’s no objection showing how he/she intends to comply with the local health and safety laws and regulations, covid-19 safety protocols/norms and other specific requirements prescribed in the contract, taking into account the supplementary information in section 6- employer’s requirements. Work shall not commence on the site until the confirmation of no objection of the SSHSMP has been obtained from the employer and is being implemented. Such confirmation of no objection by the employer shall not relive the contractor of any of his/her obligations or responsibilities under the contract. Where unanticipated health and safety hazards or risks become apparent during the contract, the contractor is required to update the SSHSMP to outline the potential impacts to site works and associated mitigation measures for the employer’s no objection. The contractor shall comply with the approved SSHSMP including covid-19 safety protocols/norms and any corrective or preventative actions set out in safeguards monitoring reports that the employer will prepare from time to time to monitor the implementation of the project emp through the SSHSMP. In particular, the contractor is required to provide all personnel on site including employer’s personnel and visitors with personal protective equipment, including protection for feet (safety boots), head, eyes, ears (safety helmets) and hands, etc., in accordance with the contractor’s SSHSMP. The contractor should ensure that his subcontractors comply with the SSHSMP and provide all such necessary equipment to their personnel. The contractor shall bear the costs to ensure that such measures, requirements and actions are carried out. The contractor shall submit monthly reports on the compliance of such measures to the employer. Replace the last sentence of the second paragraph of this Sub-Clause in its entirety by the following: “Throughout the execution and operation of the Works, the Contractor shall provide whatever is required by this person to exercise this responsibility and authority.” After the third paragraph, add the following: In the event of a significant injury involving medical treatment or hospitalization and fatal accident the contractor shall notify the employer immediately by verbal communication and submit a formal report as soon as practicable after its occurrence. For all accidents, whether fatal or not, the contractor shall also notify the appropriate local authorities in accordance with the laws of the country. In particular, the Contractor is responsible for providing site workers with safe and healthy working conditions and establish an operating system to prevent accidents, injuries, and disease. The Contractor will follow all COVID-19 protocols and safety norms at site/offices. |
| 6.8 | Contractor’s Superintendence | Replace the first paragraph of this Sub-Clause in its entirety by the following: “The Contractor shall provide all necessary superintendence to plan, arrange, direct, manage, inspect, test and monitor the design and execution of the Works and the provision of the Operation Service in accordance with his obligations under the Contract.” In the second paragraph of this Sub-Clause, after “execution of the Works” add “and the provision of the Operation Service.” |
| 6.10 | Records of Contractor’s Personnel and Equipment | Replace this Sub-Clause in its entirety by the following: “At the end of each calendar month until the end of the Operation Service Period, the Contractor shall submit to the Engineer, in a form approved by the Engineer, details showing the number of each class of Contractor's Personnel and of each type of Contractor's Equipment on the Site.” |
| Add the following entire new Clause |  |  |
| 6.25 | Gender | The Contractor shall ensure that its employees and Subcontractors observe the highest ethical standards and refrain from any form of bullying, discrimination, misconduct and harassment, including sexual harassment and shall, at all times, behave in a manner that creates an environment free of unethical behavior, bullying, misconduct and harassment, including sexual harassment. The Contractor shall take appropriate action against any employees or Subcontractors, including suspension or termination of employment or subcontract, if any form of unethical or inappropriate behavior is identified. The Contractor shall conduct training programs for its employees and Subcontractors to raise awareness on and prevent any form of bullying, discrimination, misconduct and harassment including sexual harassment, and to promote a respectful work environment. The Contractor shall keep an up-to-date record of its employees and Subcontractors who have attended and completed such training programs and provide such records to the Employer or the Engineer at their first written request. |
| CLAUSE 7 – PLANT, MATERIALS AND WORKMANSHIP |  |  |
| 7.1 | Manner of Execution | In the first paragraph of this Sub-Clause, after “execution of the Works”, add: “and provision of the Operation Service.” |
| 7.3 | Inspection | In sub-paragraph (b), after “construction (at the Site and elsewhere)”, add: “and operation and maintenance”. |
| CLAUSE 9 – TESTS ON COMPLETION |  |  |
| 9.2 | Delayed Tests | Replace the first paragraph of this Sub-Clause in its entirety by the following: “If the Tests on Completion are being unduly delayed by the Employer, Sub-Clause 10.3 [Interference with Tests on Completion] shall be applicable.” |
| CLAUSE 10 – “EMPLOYER’S TAKING OVER” shall read “COMMISSIONING” |  |  |
| Add the following entire new Clause |  |  |
| 10.1 | “Taking Over of the Works and Sections” shall read “Commissioning of the Works” | Delete the first paragraph of this Sub-Clause in its entirety, as it is not applicable. |
| 10.2 | Taking Over of Parts of the Works | This Sub-Clause shall be deleted in its entirety as it is not applicable. |
| 10.3 | Interference with Tests on Completion | This Sub-Clause shall be replaced in its entirety and replaced by the following: “If the Contractor suffers delay and/or incurs Cost as a result of a delay in carrying out the Tests on Completion which is resulting from a cause for which the Employer is responsible, the Contractor shall give notice to the Engineer and shall be entitled subject to Sub-Clause 20.1 [Contractor’s Claims] to: (a) an extension of time for any such delay, if completion is or will be delayed, under Sub-Clause 8.4 [Extension of Time for Completion], and (b) payment of any such Cost plus profit, which shall be included in the Contract Price. After receiving this notice, the Engineer shall proceed in accordance with Sub-Clause 3.5 [Determinations] to agree or determine these matters.” |
| CLAUSE 10A – OPERATION SERVICE |  |  |
| Add the following entire new Clause |  |  |
| 10A.1 | General Requirements | The Contractor shall comply with the operation management requirements as provided for in the Contract, and any Variation thereof. Prior to the commencement of the Operation Service, the Contractor shall have submitted for the Engineer’s (or Employer’s) prior approval, and obtained the Engineer’s (or Employer’s) prior approval, an Operation and Maintenance Plan as per the requirements set out in the Specification. During the whole Operation Service Period, the Contractor shall follow the requirements of the Specification, the Operation and Maintenance Plan and any operation and maintenance manual. No significant alteration to such arrangements and methods shall be made without the prior approval of the Engineer. The operators and maintenance personnel for the Works, including Plant operators, shall have the appropriate experience and qualifications to perform the Operation Service. The names, with details of their qualifications and experience, of all operation and maintenance personnel shall be submitted to the Engineer (or Employer) for approval, and no such personnel shall be engaged prior to receiving such approval. |
| 10A.2 | Commencement of Operation Service | The commencement of the Operation Service shall be from the date stated in the Commissioning Certificate issued under Sub-Clause 10.1 [Commissioning of the Works]. The Contractor shall thereafter, over the whole Operation Service Period, provide the Operation Service with the reasonable skill, care and diligence expected from an operator experienced in the operation and maintenance of Works of similar nature, size and complexity. However and additionally, for any part of the Permanent Works designed by the Contractor, the Contractor shall be responsible to ensure that this part is fit for such purposes for which the part is intended as are specified in the Contract. For the avoidance of doubt, the Contractor shall not be under any fitness for purpose obligation for a part of the Works which has not been designed by him but by (or on behalf of) the Employer. |
| 10A.3 | Raw Materials | The Employer shall be responsible for the free issue and supply and delivery to the Site (or other designated place) of the raw materials, fuels, consumables and other such items (if any) specified in the Specification. The Employer shall be responsible that all such items (if any) are fit for purpose and comply with the requirements of the Contract in respect of quality, purpose and function. In the event that any such item or product (if any) is not delivered in accordance with the agreed delivery programme or deviates from the specified quality, and such delay or deviation causes the Contractor to suffer additional cost, the Contractor shall be entitled to give due notice to the Employer of the nature of the costs which he has incurred and, subject to Sub-Clause 20.1 [Contractor's Claims], be entitled to recover his Cost plus profit. The provisions of this Sub-Clause shall not apply in cases where delays are due to: - breakdown, maintenance, repair, replacement or other operational failure under the responsibility of the Contractor; - health, safety and environmental risks carried by the Contractor; or - any act or omission of the Contractor under the Contract. All items which are: - necessary for the Operation Service; and - which are not specified as to be supplied by the Employer shall be supplied by the Contractor at his own risk. |
| 10A.4 | Training | The Contractor shall carry out the training of Employer's Personnel in the operation and maintenance of the Works to the extent specified in the Specification. The programme and scheduling of the training shall be agreed with the Employer, and the Contractor shall provide experienced training staff, and all training materials as stated in the Specification. The Employer shall be responsible for providing the training facilities and nominating and selecting suitable personnel for training. |
| 10A.5 | Delays and Interruptions during the Operation Service | Delays and interruptions during the Operation Service shall be agreed and determined as follows: - delays or interruptions caused by the Contractor If there are any delays or interruptions during the Operation Service which are caused by the Contractor, or by a cause for which the Contractor is responsible, the Contractor shall compensate the Employer for any losses including loss of revenue, loss of profit and overhead losses. The amount of compensation due shall be agreed or determined according to Sub-Clause 3.5 [Determinations], and the Employer shall be entitled to recover the amount due by making a corresponding deduction from the next payment due to the Contractor. However, the total amount of compensation payable by the Contractor to the Employer shall not exceed the amount stated in the Contract Data. - delays or interruptions caused by the Employer If there are any delays or interruptions during the Operation Service which are caused by the Employer, or by a cause for which the Employer is responsible, the Employer shall compensate the Contractor for any cost and losses including loss of revenue and loss of profit. The amount of compensation due shall be agreed or determined according to Sub-Clause 3.5 [Determinations], and the Employer shall pay the amount due by making a corresponding adjustment to the next payment due to the Contractor. In any event other than in the case of election by the Employer to terminate for his convenience pursuant to Sub-Clause 15.5 [Employer’s Entitlement to Termination for Employer's Convenience], the total amount of compensation payable by the Employer to the Contractor shall not exceed the amount stated in the Contract Data. There will be no extension of the period of the Operation Service as a result of any such delay or interruption. - Suspension by the Employer The Employer (or the Engineer) may at any time during the Operation Service instruct the Contractor to suspend progress of the Operation Service. During such suspension, the Contractor shall protect, store, secure and maintain the Plant against any deterioration, loss or damage. If the need to suspend the Operation Service by the Employer is due to any failure of the Contractor or circumstances for which the Contractor is responsible under the Contract, the provisions of paragraph (a) of this Sub-Clause shall apply. If the need to suspend the Operation Service is a result neither of any failure by the Contractor nor of circumstances for which the Contractor is responsible under the Contract, the provisions of paragraph (b) of this Sub-Clause shall apply. After the permission or instruction to resume the Operation Service is given by (or on behalf of) the Employer, the Contractor and the Employer (or the Engineer) shall jointly examine the Works. The Contractor shall make good any deterioration or defect in the Plant and the Employer (or the Engineer)shall make a written record of all making good required to be carried out by the Contractor. If the suspension is due neither to any failure by the Contractor nor to circumstances for which the Contractor is responsible under the Contract, the Contractor shall be entitled to be paid the Cost plus profit of making good the Works prior to re-commencing the Operation Service. |
| 10A.6 | Failure to Reach Production Outputs | In the event that the Contractor fails to achieve the production outputs required under the Contract, the Parties shall jointly establish the cause of such failure. - If the cause of the failure lies with the Employer or any of his servants or agents, then, after consultation with the Contractor, the Employer (or the Engineer) shall give written instruction to the Contractor of the measures which the Employer requires the Contractor to take. If the Contractor suffers any additional cost as a result of the failure or the measures instructed by the Employer (or the Engineer), the Employer, subject to Sub-Clause 3.5 [Determinations] and Sub-Clause 20.1 [Contractor's Claims], shall pay the Contractor his Cost plus profit. - If the cause of the failure lies with the Contractor then, after due consultation with the Employer, the Contractor shall take all steps necessary to restore the output to the levels required under the Contract. If the Employer suffers any loss as a result of the failure or the measures taken by the Contractor, the Employer shall have the same remedies as provided under Sub-Clause 10A.5(a). If the failure continues for a period of more than 84 days and the Contractor is unable to achieve the required production output, the Employer may either: - continue with the Operation Service at a reduced level of compensation determined in accordance with Sub-Clause 3.5 [Determinations]; or - if the production outputs fail to reach the minimum values required in the Contract Data, give notice to the Contractor not less than 56 days prior to terminating the Contract, in accordance with Sub-Clause 15.2 [Termination by Employer]. In such an event, the Employer shall be free to continue the Operation Service himself or by others. |
| 10A.7 | Completion of Operation Service | The obligation of the Contractor to operate and maintain the Works under the Operation Service shall cease at the end of the period stated in the Contract as the Operation Service Period. Notwithstanding the foregoing, other services to be performed by the Contractor must be completed before the Contractor will be entitled to receive the Performance Certificate in accordance with Sub-Clause 11.9 [Performance Certificate]. Other pre-conditions which must be fulfilled by the Contractor before the Performance Certificate will be issued are: - Updating Operation and Maintenance Plan, and operation and maintenance manuals providing performance records and data; - Supply of all Contractor’s Documents; and - Completion and testing of all of the Works, including remedying any defects, All in accordance with the Contract. |
| 10A.8 | Ownership of Output and Revenue | During the Operation Service, any production output and revenue shall be the exclusive property of the Employer. |
| CLAUSE 11 – DEFECTS LIABILITY |  |  |
| 11.1 | Completion of Outstanding Works and Remedying Defects | In sub-paragraph (b) of this Sub-Clause, replace: “execute all work required to remedy defects or damage, as may be notified by (or on behalf of) the Employer on or before the expiry date of the Defects Notification Period for the Works or Section (as the case may be)” by the following: “repair and make good any damage or defect occurring during the Operation Service Period, whether such defect or damage is notified by(or on behalf of) the Employer, or observed by the Contractor himself.” |
| 11.2 | Cost of Remedying Defects | Add the following at the end of the sub-clause: Upon the completion of construction, the Contractor shall fully reinstate pathways, other local infrastructure, and agricultural land to at least their pre-project condition as recorded by the Contractor in consonance with its obligation in Clause 4.16. |
| 11.3 | Extension of Operation Service Period | Add the following at the end of the first paragraph of this Sub-Clause: “Any extension of the Operation Service Period under this Sub-Clause shall be carried out at the cost of the Contractor and shall not give rise to any payment from the Employer to the Contractor.” |
| 11.9 | Performance Certificate | Delete the second paragraph of this Sub-Clause in its entirety, and replace it with the following: “The Engineer (or the Employer) shall issue the Performance Certificate as soon as after the latest of the expiry dates ofthe Operation Service Periods, and the Contractor has fulfilled all pre-conditions set out under Sub-Clause 10A.7 [Completion of Operation Service].” |
| CLAUSE 13 – VARIATIONS AND ADJUSTMENTS |  |  |
| 13.1 | Right to Vary | Insert the following paragraph as last paragraph under this Sub-Clause: “If the Employer or the Engineer wishes to instruct a Variation during the Operation Service Period, he shall give the Contractor written details of his requirements. The Contractor shall then proceed in accordance with Sub-Clause 13.3 [Variation Procedure] sub-paragraphs (a), (b) and (c). However, the Contractor shall not be obliged to proceed with the Variation until the matters covered in Sub-Clause 13.3 [Variation Procedure] sub-paragraphs (a), (b) and (c) have been agreed between the Employer and the Contractor.” |
| 13.8 | Adjustments for Changes in Costs | Replace the last but one paragraph in its entirety by the following: “If the Contractor fails to complete the Works within the Time for Completion, adjustment of pricesthereafter shall be made by reference to the indices or prices which would have been applicable had the Contractor completed the Works on the Time for Completion.” |
| CLAUSE 14 – CONTRACT PRICE AND PAYMENT |  |  |
| 14.9 | Payment of Retention Money | Replace the third paragraph in its entirety by the following: “However, if any work remains to be executed under Clause 11 [Defects Liability] or Sub-Clause 10A.7 [Completion of Operation Service], the Engineer shall beentitled to withhold certification of the estimated cost of this work until it has been executed.” |
| CLAUSE 15 – TERMINATION BY EMPLOYER |  |  |
| 15.2 | Termination by Employer | Replace sub-paragraph (c)(i) in its entirety by the following: “(i) to proceed with the Works in accordance with Clause 8 [Commencement, Delays and Suspension] or to proceed with the Operation Service in accordance with Clause 10A [Operation Service], or.” In last but one paragraph, replace the first sentence in its entirety by the following: “After termination, the Employer may complete the Works and provide the Operation Service and/or arrange for any other entities to do so.” |
| 15.5 | Employer’s Entitlement to Termination for Convenience | Replace the last sentence of the first paragraph in its entirety by the following: “The Employer shall not terminate the Contract under this Sub-Clause in order to execute or operate the Works (or any part thereof) himself, or arrange for the Works (or any part thereof) to be executed by another contractor or to avoid a terminationof the Contract by the Contractor under Clause 16.2 [Termination by Contractor]”. |
| CLAUSE 17 – RISK AND RESPONSIBILITY |  |  |
| 17.1 | Indemnities | In sub-paragraphs (a) and (b), after “completion of the Works”, add: “and the provision of the Operation Service”. |
| 17.2 | Contractor’s Care of the Works | Replace the two first paragraphs in their entirety by the following: “The Contractor shall take full responsibility for the care of the Works, Goods and Contractor’s Documents from the Commencement Date until the Performance Certificate is issued, when responsibility for the care of the Works shall pass to the Employer.” In the last paragraph, replace any reference to “Taking-Over Certificate” by a reference to “Performance Certificate”. |
| 17.6 | Limitation of Liability | Replace the first paragraph in its entirety by the following: “Neither Party shall be liable to the other Party for loss of use of any Works, loss of profit, loss of anycontract or for any indirect or consequential loss or damage which may be suffered by the other Party inconnection with the Contract, other than as specifically provided in Sub-Clause 8.7 [Delay Damages]; Sub-Clause 10A.5 [Delays and Interruptions during the Operation Service]Sub-Clause 11.2 [Cost of Remedying Defects]; Sub-Clause 15.4 [Payment after Termination]; Sub-Clause16.4 [Payment on Termination]; Sub-Clause 17.1 [Indemnities]; Sub-Clause 17.4(b) [Consequences of Employer’s Risks] and Sub-Clause 17.5 [Intellectual and Industrial Property Rights].” |
| CLAUSE 18 – INSURANCE |  |  |
| 18.1 | General Requirements for Insurances | In sub-paragraph (b), after “Sub-Clause 18.3 [Insurance against Injury to Persons and Damage to Property]”, add: “and Sub-Clause 18.5 [Insurances for Operation Service]”. |
| 18.2 | Insurance for Works and Contractor’s Equipment | In the first paragraph of this Sub-Clause, replace “Taking-Over Certificate for the Works” by “Performance Certificate” Delete the second paragraph of this Sub-Clause in its entirety as it is not applicable. Delete sub-paragraph (e)(iii) in its entirety as it is not applicable. |
| 18.3 | Insurance against Injury to Persons and Damage to Property | In sub-paragraph (d)(ii) of this Sub-Clause, after “execute the Works”, add: “, provide the Operation Service”. |
| 18.4 | Insurance for Contractor’s Personnel | In last paragraph of this Sub-Clause, after “execution of the Works”, add: “and the provision of the Operation Service.”. |
| 18.5 | Insurances for Operation Service | Add the following new Sub-Clause: “The Contractor shall provide the following insurances during the Operation Service Period: - Fire extended cover for the Works The Contractor shall provide, in the joint names of the Employer and the Contractor, fire extended cover insurance for the Works as specified in the Contract Data for the Operation Service Period. Notwithstanding any other provision in the Contract, the Operation Service shall not commence until the fire extended cover insurance is effected and the terms and details have been approved by the Employer. The terms of the policy shall be submitted to the Employer for his approval no later than 28 days before the date upon which the Commissioning Certificate is due to be issued, and shall come into force on the date stated in the Commissioning Certificate. - Liability for breach of professional duty The Contractor shall insure the legal liability of the Contractor arising out of the negligent fault, defect, error or omission of the Contractor or any person for whom the Contractor is responsible in the carrying out their professional duties in an amount not less than that stated in the Contract Data. The Contractor shall maintain this insurance for the period specified in the Contract Data. - Other insurances required by Laws and local practice Other insurances required by Laws and by local practice (if any) shall be detailed in the Contract Data and the Contractor shall provide such insurances in compliance with the details given, at his own cost.” |
| CLAUSE 20 – CLAIMS, DISPUTES AND ARBITRATION |  |  |
| 20.4 | Obtaining Dispute Board’s Decision | In the first paragraph of this Sub-Clause, after “execution of the Works”, add: “or the provision of the Operation Service” |
| 20.6 | Arbitration | Delete the last paragraph in its entirety and replace it with the following: “Arbitration may be commenced prior to or after completion of the Works or of the Operation Service. The obligations of the Parties, the Engineer and the DB shall not be altered by reason of any arbitration being conducted during the progress of the Works or of the Operation Service.” |
| 20.8 | Expiry of Dispute Board’s Appointment | In this Sub-Clause, after “execution of the Works”, add: “or the provision of the Operation Service” |

- Part B – Specific Provisions

The Particular Conditions of Contract (PCC) Part B - Specific provisions, is to amend or for additions to the General Conditions of Contract (GCC-Section 7). Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| 4 | The Contractor |
| --- | --- |
| 4.8 | Safety Procedures (a) comply with all applicable safety regulations, (b) take care for the safety of all persons entitled to be on the Site, The Contractor is responsible for providing site workers with safe and healthy working conditions and establish an operating system to prevent accidents, injuries, and disease, and report to the employer. (c ) use reasonable efforts to keep the Site and Works clear of unnecessary obstruction so as to avoid danger to these persons, (d) provide fencing, lighting, guarding and watching of the Works until completion and taking over under Clause 10 [Employer’s Taking Over ], and (e) provide any Temporary Works (including roadways, footways, guards and fences) which may be necessary, because of the execution of the Works, for the use and protection of the public and of owners and occupiers of adjacent land. |
| 4.12 | Unforeseeable Physical Conditions “In addition to notice of any Unforeseeable Physical Conditions, the Contractor shall provide the Engineer with a written notice of any unanticipated environmental, resettlement or indigenous peoples risk, or impact that arise during construction, implementation or operation of the Project that were not considered in the Initial Environmental Examination (IEE) the RP or the IPP, attached thereto as Appendix 1 through Appendix 5.” |
| 4.13 | Right of Way and Facilities “The Contractor shall comply with (i) the measures and requirements relevant to the Contractor which are set forth in the Resettlement Plan (“RP”) attached hereto as Appendix [1_], to the extent it concerns impacts on affected people during construction; and (ii) any corrective or preventive actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor implementation of the resettlement plan. The Contractor shall allocate a budget for compliance with these measures, requirements and actions.” Setting Out “The Contractor shall comply with (i) the measures and requirements set forth in the Resettlement Plan (RP) and Indigenous People Plan (IPP) attached there to as Appendix 1 & Appendix 2, to the extent they concern impacts on affected people during construction; and (ii) any corrective or preventive actions set out in a Safeguards Monitoring Report (SMR) that the Employer will prepare from time to time to monitor implementation of (RP). The Contractor shall allocate a budget for compliance with these measures, requirements and actions.” |
| 4.16 | Transport of Goods Add the following at the end of Sub-clause 4.16(d) as: “The Contractor shall adequately record the condition of roads, agricultural land and other infrastructure prior to the start of transporting materials, goods, and equipment, and construction.” |
| 4.18 | Protection of the Environment “At the end of the sub-clause in 4.18 Protection of the Environment, add the following paragraphs:” “Without prejudice to any other obligation under or in connection with the Contract, the Contractor shall comply with all environmental requirements stated in the Employer’s Requirements, and in particular with those which may be set forth in the initial environmental examination and environmental management plan, as well as in any safeguards monitoring report of the project which may be included in the Employer’s Requirements.” - “The Contractor shall comply with all applicable national, provincial, and local environmental laws and regulations. - The Contractor shall also comply with all reasonable requests of the national and local authorities responsible for enforcing environmental controls. - Within 28 days of the Commencement Date the Contractor shall submit a detailed Site Specific Environmental Management Plan (SSEMP) for the Engineer’s no objection showing how he/she intends to comply with environmental laws and regulations and other specific requirements prescribed in the Contract, addressing all the monitoring and mitigation measures set forth in the Environmental Impact Assessment (“EIA”) and the Environmental Management Plan (“EMP”) of the project attached in Section 6- Employer’s Requirements. Work shall not commence on the Site until the no objection of SSEMP has been obtained from the Engineer and is being implemented. Such acceptance by the Engineer shall not relive the Contractor of any of his obligations or responsibilities under the Contract. - The Contractor shall (a) establish an operational system for managing environmental impacts, (b) comply with the approved SSEMP and any corrective or preventative actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor the implementation of the project EMP through the SSEMP, (c) allocate the budget required to ensure that such measures, requirements and actions are carried out, (d) submit semi-annual reports on the compliance of such measures to the Employer. Where unanticipated environmental risks or impacts become apparent during the Contract, the Contractor is required to update the SSEMP to outline the potential impacts to site works and associated mitigation measures for the Engineer’s approval.” |
| 4.21 | (i) “monitoring of the obligations in Sub-Clauses 4.8, 4.12, 4.13, 4.16, 4.18, 6.4, 6.7 and 6.21” |
| 6 | Staff and Labour |
| 6.4 | Labour Laws “The Contractor shall not make employment decisions based upon personal characteristics unrelated to job requirements. The contractor shall follow and implement all statutory provisions on labour (including not employing or using children as labour and equal pay for equal work), health, safety, welfare, sanitation and working conditions. The Contractor shall base the employment relationship upon equal opportunity and fair treatment, and shall not discriminate with respect to aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment or retirement, and discipline. The Contractor shall provide equal wages and benefits to men and women for the work of equal value or type.” |
| 6.6 6.7 | Facilities for Staff and Labours Except as otherwise stated in the Specification, the Contractor shall provide and maintain all necessary accommodation and welfare facilities for the Contractor’s Personnel. The Contractor shall also provide facilities for the Employer’s Personnel as stated in the Specification. The Contractor shall not permit any of the Contractor’s Personnel to maintain any temporary or permanent living quarters within the structures forming part of the Permanent Works. The labor camp should be constructed following the standards outlined in the IFC and EBRD Accommodation Guidance Note [(can be found in this link: Workers' Accommodation: Processes and Standards (ifc.org)], including hygienic facilities with proper ablution facilities, waste management. No camp facilities should be located within areas considered at risk of flooding or natural hazards. The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. In collaboration with local health authorities, the Contractor shall ensure that medical staff, first aid facilities, sick bay and ambulance service are available at all times at the Site and at any accommodation for Contractor’s and Employer’s Personnel, and that suitable arrangements are made for all necessary welfare and hygiene requirements and for the prevention of epidemics. “After the first paragraph, add the following:” The contractor is responsible for establishment of preventive and emergency preparedness and response measures to avoid, and where avoidance is not possible, to minimize, adverse impacts and risks of the construction site work to the health and safety of local communities. Within 28 days of the commencement date the contractor shall submit a detailed site specific health and safety management plan (SSHSMP), including HS-C19 Plan, for the employer’s no objection showing how he/she intends to comply with the local health and safety laws and regulations, covid-19 safety protocols/norms and other specific requirements prescribed in the contract, taking into account the supplementary information in section 6- employer’s requirements. Work shall not commence on the site until the confirmation of no objection of the SSHSMP has been obtained from the employer and is being implemented. Such confirmation of no objection by the employer shall not relive the contractor of any of his/her obligations or responsibilities under the contract. Where unanticipated health and safety hazards or risks become apparent during the contract, the contractor is required to update the SSHSMP to outline the potential impacts to site works and associated mitigation measures for the employer’s no objection. The contractor shall comply with the approved SSHSMP including covid-19 safety protocols/norms and any corrective or preventative actions set out in safeguards monitoring reports that the employer will prepare from time to time to monitor the implementation of the project emp through the SSHSMP. In particular, the contractor is required to provide all personnel on site including employer’s personnel and visitors with personal protective equipment, including protection for feet (safety boots), head, eyes, ears (safety helmets) and hands, etc., in accordance with the contractor’s SSHSMP. The contractor should ensure that his subcontractors comply with the SSHSMP and provide all such necessary equipment to their personnel. The contractor shall bear the costs to ensure that such measures, requirements and actions are carried out. The contractor shall submit monthly reports on the compliance of such measures to the employer. The Contractor shall send, to the Engineer, details of any accident as soon as practicable after its occurrence. The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Engineer may reasonably require. HIV-AIDS Prevention. The Contractor shall conduct an HIV-AIDS awareness programme via an approved service provider, and shall undertake such other measures as are specified in this Contract to reduce the risk of the transfer of the HIV virus between and among the Contractor’s Personnel and the local community, to promote early diagnosis and to assist affected individuals. In the event of a significant injury involving medical treatment or hospitalization and fatal accident the contractor shall notify the employer immediately by verbal communication and submit a formal report as soon as practicable after its occurrence. For all accidents, whether fatal or not, the contractor shall also notify the appropriate local authorities in accordance with the laws of the country. In particular, the Contractor is responsible for providing site workers with safe and healthy working conditions and establish an operating system to prevent accidents, injuries, and disease. The Contractor will follow all COVID-19 protocols and safety norms at site/offices. The Contractor shall throughout the contract (including the Defects Notification Period): (i) conduct Information, Education and Communication (IEC) campaigns, at least every other month, addressed to all the Site staff and labour (including all the Contractor's employees, all Subcontractors and any other Contractor’s or Employer’s personnel, and all truck drivers and crew making deliveries to Site for construction activities) and to the immediate local communities, concerning the risks, dangers and impact, and appropriate avoidance behaviour with respect to, of Sexually Transmitted Diseases (STD) - or Sexually Transmitted Infections (STI) in general and HIV/AIDS in particular; (ii) provide male or female condoms for all Site staff and labour as appropriate; and (iii) provide for STI and HIV/AIDS screening, diagnosis, counselling and referral to a dedicated national STI and HIV/AIDS programme, (unless otherwise agreed) of all Site staff and labour. |
| 6.20 | Forced Labour The Contractor shall not employ forced labour, which consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labour, such as indentured labour, bonded labour or similar labour-contracting arrangements. |
| 6.21 | Child Labour Replace the Sub-clause 6.21 with the following: “The Contractor shall not employ any child to perform any work, including work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, moral, or social development. “Child” means a child below the statutory minimum age specified under applicable National, provincial or local law.” |
| 6.25 | Gender The Contractor shall comply with the measures set forth in the gender equality and social inclusion action plan attached hereto as Appendix [6]." “The Contractor shall ensure that its employees and Subcontractors observe the highest ethical standards and refrain from any form of bullying, discrimination, misconduct and harassment, including sexual harassment and shall, at all times, behave in a manner that creates an environment free of unethical behavior, bullying, misconduct and harassment, including sexual harassment. The Contractor shall take appropriate action against any employees or Subcontractors, including suspension or termination of employment or subcontract, if any form of unethical or inappropriate behavior is identified. The Contractor shall conduct training programs for its employees and Subcontractors to raise awareness on and prevent any form of bullying, discrimination, misconduct and harassment including sexual harassment, and to promote a respectful work environment. The Contractor shall keep an up-to-date record of its employees and Subcontractors who have attended and completed such training programs and provide such records to the Employer or the Engineer at their first written request.” |
| 11.2 | “Add the following at the end of the sub-clause:” |

- Upon the completion of construction, the Contractor shall fully reinstate pathways, other local infrastructure, and agricultural land to at least their pre-project condition as recorded by the Contractor in consonance with its obligation in Clause 4.16.

.

Whether as a Contractor, Subcontractor, Consultant, Manufacturer or Supplier, or Service Provider; or in any other capacity (different names are used depending on the particular Bidding Document).