Section 6 - Employer’s Requirements

This Section contains the Specifications, Drawings, Supplementary Information that describe the Works to be procured, Personnel Requirements, and Equipment Requirements.

Table of Contents

Specifications	6-2

Drawings	6-3

Supplementary Information Regarding Works to Be Procured	6-4

Personnel Requirements	6-8

Equipment Requirements	6-9

Environmental Safegaurds	6-10

List of Appndix	6-12

Appndix 1	6-13

Appndix 2	6-14

Appndix 3	6-15

Appndix 4	6-16

Appndix 5	6-17

Undertaking	6-20

Additional Conditions	6-21

Specifications

Attached Separately

Drawings

Attached Separately

Supplementary Information

Regarding Works to Be Procured

Attached Separately

### Mile stones

| Sl. No. | Description of work | Milestone I (6 months) | Milestone II (12 months) |  | Milestone III (18 months) |  | Milestone IV (24 months) |  |  | Milestone V (30 months) |  | Milestone VI (36 months) |  | Milestone VII (42 months) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Survey and confirmation of levels | Entire sewer network |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Collection System for all Zones which includes Gravity Sewer, Machine-hole, Narrow, Streets, Railway, Road crossings (in KM) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (a) | DWC Pipes (Km) | 25.00 | 60.00 |  | 100.00 |  | 150.00 |  |  | 200.00 |  | 243.44 |  |  |
| (b) | CI Pipes (Km) | 2.00 | 8.00 |  | 20.00 |  | 32.00 |  |  | 44.00 |  | 55.50 |  |  |
| 3 | Main pumping stations, Lift stations and pumping stations |  | Wells, Pit, Chamber, Pump room & compound wall all works such as plastering, white washing, colour washing etc., for 1 No. |  | Wells, Pit, Chamber, Pump room & compound wall all works such as plastering, white washing, colour washing etc., for 2 Nos. |  | Wells, Pit, Chamber, Pump room & compound wall all works such as plastering, white washing, colour washing etc., for 3 Nos. |  |  | Wells, Pit, Chamber, Pump room & compound wall all works such as plastering, white washing, colour washing etc., for 4 Nos |  | Wells, Pit, Chamber, Pump room & compound wall all works such as plastering, white washing, colour washing etc., for 5 Nos |  |  |
| 4 | Sewerage Non Clog Pumpset & DG sets for all Pumping/ Lifting stations |  |  |  | Supply 50% |  | Supply 100% |  |  | Erection 50% |  | Erection 100% |  |  |
| 5 | Pumping main CI Pipes |  | 0.50 |  | 1.00 |  | 2.00 |  |  | 3.00 |  | 3.95 |  |  |
| 6 | Odour Control device |  |  |  |  |  |  |  |  | Supply & erection 50% |  | Supply & erection 100% |  |  |
| 7 | House service connection including chambers | 1000 |  | 5000 |  | 13000 |  | 22000 | 32000 |  | 42576 |  |  |  |
| 8 | Road restora-tion for House Service Connection |  |  | 5% |  | 25% |  | 50% | 75% |  | 100% |  |  |  |
| 9 | Road restora-tion for collection system |  |  | 5% |  | 25% |  | 50% | 75% |  | 100% |  |  |  |
| 10 | Trial Run and Commissioning |  |  |  |  |  |  |  |  |  |  |  | 100% |  |

The contractor is required to follow local regulations and guidance specific to COVID-19 prevention and controls, and worksite safety measures requirements that are deemed applicable to the contract

The following Standard Operating Procedure issued by the Government of TamilNadu should be strictly adhered to by the contractor without any lapse.

Personnel Requirements

Using Form PER - 1 and PER - 2 in Section 4 (Bidding Forms), the Bidder must demonstrate that it has personnel who meet the following requirements:

| No. | Position | No.of persons | Total Work Experience [years] | Experience In Similar Work [years] |
| --- | --- | --- | --- | --- |
| 1 | Project Manager Graduate in Civil Engineering/ Project Management/ Construction Management | 1 | 15 | 10 |
| 2 | Process Engineer Graduate in Civil Engineering/ Project Management/ Construction Management | 2 | 10 | 5 |
| 3 | Mechanical/Electrical Engineer Graduate in Mechanical/Electrical Engineering | 1 | 10 | 5 |
| 4 | Quality Control Engineer Graduate Civil Engineer | 2 | 10 | 5 |
| 5 | Environmental Safeguard Officer (Covering both environmental and social safeguard has to be deployed) Graduate Environmental Science, Engineering/ Planning and related field with EHS Certification | 2 | 5 | 3 |
| 6 | Safety / Accident Prevention Officer Graduate and Suitably qualified to ensure safety and accident prevention at works | 2 | 5 | 3 |
| 7 | Project Engineer Graduate Civil Engineer | 5 | 10 | 5 |
| 8 | Senior Engineer | 10 | 5 | 3 |
| 9 | Staff for site testing and operation | 2 | 5 | 3 |

Equipment Requirements

Using Form EQU in Section 4 (Bidding Forms), the Bidder must demonstrate that it has the key equipment listed below:

| Sl. No. | Equipment Type and Characteristics | Capacity | Minimum Number Required |
| --- | --- | --- | --- |
| 1 | Trench Excavators | 0.5 Cum./Each | 5 |
| 2 | Pavement Breakers | 5 T/Each | 3 |
| 3 | Dewatering Pumps | Various capacity (5 to 10 HP) | 3 |
| 4 | Lifting Rig/ Derrick with Chain pulley | 5 T/Each | 3 |
| 5 | Concrete Mixer | 10 Cft./Each | 4 |
| 7 | Mechanical Earth Compactor | 4 T/Each | 4 |
| 8 | Truck | 6 to 10 T/Each | 3 |
| 9 | Hydraulic Mobile Crane (6 MT) | Boom Ht. 6 m (20 T)Each | 2 |
| 10 | Mobile DG set | 100 KVA | 2 |
| 11 | Needle Vibrator | 20 to 50mm needle | 6 |
| 12 | Pipe cutting machine | --- | 6 |
| 13 | Electrical earth tester | 500 Volt. | 4 |
| 14 | Megger | 500 Volt. | 5 |
| 15 | Equipment for site testing |  | 2 |

Environmental safeguards - Initial Environmental Examination (IEE) / Environmental Management Plan (EMP)

An Initial Environmental Examination (IEE) has been carried out to assess the environmental impacts and provide mitigation and monitoring measures to ensure that there are no significant impacts as a result of the project. An environmental management plan (EMP) has been developed to provide mitigation measures to reduce all negative impacts to acceptable levels. Locations and site-selection of the proposed infrastructures were considered to further reduce impacts. IEE and EMP is attached at Appendix 5 and Appendix 4.

- The Initial Environment Examination Report, including the EMP, forms part of the Contract. It is the responsibility of the contractor to review the requirements in the IEE Report, including the EMP, and comply with all its provisions.

- Prior to commencement of the works, the contractor will submit a compliance report to Employer’s Representative that all identified pre-construction mitigation measures as detailed in the EMP are undertaken. Contractor should confirm that the resources for EMP compliance are mobilized.

- The Contractor shall mobilize on site the necessary staff resources on full time basis to implement the EMP including health and safety measures (a) Environmental safeguards officer and (b) accident prevention officer.

- The Contractor shall prepare and submit to the Employer, for review and approval, a Site-specific Environmental Management Plan (SEMP) consistent with the Environmental Management Plan (EMP) in the IEE, including site-specific Health and Safety Management Plan (SHMP) in accordance with the H&S COVID-19 Plan (HS-C19 Plan) submitted during the bidding process and updated as necessary. The SEMP shall include (i) proposed sites/locations for construction work camps, storage areas, hauling roads, laydown areas, disposal areas for solid and hazardous wastes; (ii) specific mitigation measures following the approved EMP; (iii) monitoring program as per SEMP; and (iv) budget for SEMP implementation. No works are allowed to commence prior to approval of SEMP.

- No civil works shall commence until the Site-specific Environmental Management Plan (SEMP), including Health & Safety Plan (SHMP) is approved by the Employer.”

- A copy of the EMP and approved SEMP will be kept on site during the construction period at all times. The EMP forms part of the of contract agreement. Non-compliance with, or any deviation from, the conditions set out in this document constitutes a failure in compliance.

- For civil works, the contractor will be required to (i) carry out all of the mitigation and monitoring measures set forth in the approved SEMP; and (ii) implement any corrective or preventative actions set out in safeguards monitoring reports that the employer will prepare from time to time to monitor implementation of this IEE and SEMP. The contractor shall allocate budget for compliance with these SEMP measures, requirements and actions.

- In order to prevent environmental pollution arising from the construction activities related to the performance of this Contract, the Contractor shall comply with all applicable local laws and regulations concerning pollution and waste material disposal, including the SEMP and monitoring plan in the EMP, as well as the specific requirements stated in this section and elsewhere in the Specifications.”

- During construction and operation, results from internal monitoring by the contractor will be reflected in their monthly EMP implementation reports submitted to the Employer’s Representative.

- The contractor shall arrange training programs to all the employees engaged by him on safety measures with suitable institutions at his own cost.

Contractor shall obtain all approvals, consents and permits as required under applicable law to enter into this Contract and undertake the Project

Resettlement plan is attached to Appendix 1.

The following requirements specified in the resettlement planning document and/or the EMP will have to be ensured by the contractor:

- Impact avoidance measures if any mentioned in the RP (e.g. provision of access planks, and planks with handrails in case of excavations exceeding 1m depth and/or 1 m width) will be strictly adhered to, and documented photographically;

- GRM requirements (provision of grievance registers and signages depicting construction schedule and with contact numbers for grievance registration at all construction sites) will be ensured;

Unanticipated impacts during construction will be reported to PIU within 24 hours, and corrective action taken as advised by PIU/PMU.

IEE and RP are provided as supplementary information and attached to the bid documents

List of Appendix

Appendix 1:	Resettlement Plan

Appendix 2:	Indigenous Peoples Plan

Appendix 3:	Initial Environmental Examination (IEE) Report

including Environmental Management Plan

Appendix 4:	Gender Equality and Social inclusion Action Plan

Appendix 5:	Salient Features of Labour & Environment

Protection

Appendix 1

Resettlement Plan

Attached Separately

Appendix 2

Indigenous Peoples Plan (IPP)

Attached Separately

Appendix 3

Initial Environmental Examination (IEE) Report

including Environmental Management Plan

Attached Separately

# Appendix 4

# Gender Equality and Social inclusion Action Plan

Appendix 5

Salient Features of Labour & Environment Protection

SALIENT FEATURES OF SOME MAJOR LABOUR LAWS

APPLICABLE TO ESTABLISHMENTS ENGAGED IN BUILDING AND OTHER CONSTRUCTION WORK

  - Employees Compensation Act 1923: The Act provides for compensation in case of injury, disease or death arising out of and during the course of employment.

  - Payment of Gratuity Act 1972: gratuity is payable to an employee under the Act on satisfaction of certain conditions on separation if an employee has completed 5 years’ service or more or on death at the rate of 15 days wages for every completed year of service.  The Act is applicable to all establishments employing 10 or more employees.

  - Employees P.F. and Miscellaneous Provision Act 1952 (since amended):  The Act provides for monthly contribution by the employer plus workers @ 10% or 8.33%.  The benefits payable under the Act are:

(i)	Pension or family pension on retirement or death, as the case may be.

(ii)	Deposit linked insurance on the death in harness of the worker.

(iii)Payment of P.F. accumulation on retirement/death etc.

  - Maternity Benefit Act 1961:  The Act provides for leave and some other benefits to women employees in case of confinement or miscarriage etc.

  - Sexual Harassment of Women at the Workplace (Prevention, Prohibition and Redressal) Act, 2013: This Act defines sexual harassment in the workplace, provides for an enquiry procedure in case of complaints and mandates the setting up of an Internal Complaints Committee or a Local Complaints Committee

  - Contract Labour (Regulation & Abolition) Act 1970: The Act provides for certain welfare measures to be provided by the Contractor to contract labour and in case the Contractor fails to provide, the same are required to be provided, by the Principal Employer by law.  The Principal Employer is required to take Certificate of Registration and the Contractor is required to take license from the designated Officer.  The Act is applicable to the establishments or Contractor of Principal Employer if they employ 20 or more contract labour.

  - Minimum Wages Act 1948:  The Employer is supposed to pay not less than the Minimum Wages fixed by appropriate Government as per provisions of the Act if the employment is a scheduled employment.  Construction of Buildings, Roads, Runways are scheduled employments.

  - Payment of Wages Act 1936:  It lays down the mode, manner and by what date the wages are to be paid, what deductions can be made from the wages of the workers.

  - Equal Remuneration Act 1976:  The Act provides for payment of equal wages for work of equal nature to male and female workers and for not making discrimination against Female employees in the matters of transfers, training and promotions etc.

  - Payment of Bonus Act 1965:  The Act is applicable to all establishments employing 20 or more employees. Some of the State Governments have reduced this requirement from 20 to 10. The Act provides for payments of annual bonus subject to a minimum of 8.33% of the wages drawn in the relevant year. It applies to skilled or unskilled manual, supervisory, managerial, administrative, technical or clerical work for hire or reward to employees who draw a salary of Rs. 10,000/- per month or less. To be eligible for bonus, the employee should have worked in the establishment for not less than 30 working days in the relevant year.    The Act does not apply to certain establishments.

  - Industrial Disputes Act 1947:  the Act lays down the machinery and procedure for resolution of Industrial disputes, in what situations, a strike or lock-out becomes illegal and what are the requirements for laying off or retrenching the employees or closing down the establishment.

  - Trade Unions Act 1926:  The Act lays down the procedure for registration of trade unions of workmen and employers.  The Trade Unions registered under the Act have been given certain immunities from civil and criminal liabilities.

  - Child Labour (Prohibition & Regulation) Act 1986:  The Act prohibits employment of children below 14 years of age in certain occupations and processes and provides for regulation of employment of children in all other occupations and processes.  Employment of Child Labour is prohibited in the Building and Construction Industry.

  - Inter-State Migrant workmen’s (Regulation of Employment & Conditions of Service) Act 1979:  The Act is applicable to an establishment which employs 5 or more inter-state migrant workmen through an intermediary (who has recruited workmen in one state for employment in the establishment situated in another state).  The Inter-State migrant workmen, in an establishment to which this Act becomes applicable, are required to be provided certain facilities such as housing, medical aid, traveling expenses from home upto the establishment and back,etc.

  - The Building and Other Construction Workers (Regulation of Employment and Conditions of Service) Act 1996 and the Building and Other Construction Workers Welfare Cess Act, 1996 (BOCWW Cess Act):  All the establishments who carry on any building or other construction work and employ 10 or more workers are covered under these Acts.  All such establishments are required to pay cess at the rate not exceeding 2% of the cost of construction as may be notified by the Government.  The Employer of the establishment is required to provide safety measures at the building or construction work and other welfare measures, such as Canteens, First –Aid facilities, Ambulance, Housing accommodations for workers near the work place etc.  The Employer to whom the Act applies has to obtain a registration certificate from the Registering Officer appointed by the Government.

  - Factories Act 1948:  the Act lays down the procedure for approval of plans before setting up a factory engaged in manufacturing processes, health and safety provisions, welfare provisions, working hours, annual earned leave and rendering information regarding accidents or dangerous occurrences to designated authorities.  It is applicable to premises employing 10 persons or more with aid of power or 20 or more persons without the aid of power.

  - Weekly Holidays Act -1942

  - Bonded Labour System (Abolition) Act, 1976: The Act provides for the abolition of bonded labour system with a view to preventing the economic and physical exploitation of weaker sections of society. Bonded labour covers all forms of forced labour, including that  arising out of a loan, debt or advance.

  - Employer’s Liability Act, 1938: This Act protects workmen who bring suits for damages against employers in case of injuries endured in the course of employment. Such injuries could be on account of negligence on the part of the employer or persons employed by them in maintenance of all machinery, equipment etc. in healthy and sound condition.

  - Employees State Insurance Act 1948: The Act provides for certain benefits to insured employees and their families in case of sickness, maternity and disablement arising out of an employment injury. The Act applies to all employees in factories (as defined) or establishments which may be so notified by the appropriate Government. The Act provides for the setting up of an Employees’ State Insurance Fund, which is to be administered by the Employees State Insurance Corporation. Contributions to the Fund are paid by the employer and the employee at rates as prescribed by the Central Government. The Act also provides for benefits to dependents of insured persons in case of death as a result of an employment injury.

  - The Personal Injuries (Compensation Insurance) Act, 1963: This Act provides for the employer’s liability and responsibility to pay compensation to employees where workmen sustain personal injuries in the course of employment.

  - Industrial Employment (Standing Order) Act 1946:  It is applicable to all establishments employing 100 or more workmen (employment size reduced by some of the States and Central Government to 50).  The Act provides for laying down rules governing the conditions of employment by the Employer on matters provided in the Act and get the same certified by the designated Authority.

UNDERTAKING

1.      I/We ...........................        (Name, Age, Father’s name and address of the contractor) are aware of the directions of the Hon’ble High Court of Madras in its order-dated 20.11.2008 in W.P.No. 24403/2008, and the orders of the government of Tamil Nadu in G.O (MS) No. 293, M.A & W.S (MW) Department, dated 26.11.2010, regarding the ban on manual scavenging and on the entry of sanitary workers into the sewerage system  I/ We undertake to abide by the said directions of the High Court and Government order in this regard.

2. I/We shall not allow sanitary workers to enter into the sewerage system for cleaning or maintenance operations except in the 4 circumstances permitted in the orders of the High Court in W.P.No. 24403, dated 20.11.2008.  I/ we am/are aware that even in these 4 circumstances.  I/ we should allow the workers to enter only with adequate safety gadgets and under the supervision of a qualified staff, and only after duly observing all safety precautions including testing for the presence of toxic gases.

3. I/We are aware that violation of the said directions of the Hon’ble High Court and the G.O will attract punishment under section 14 of the Employment of Manual Scavengers and Construction of Dry Latrines (Prohibition) Act 1993.

Signature of the Contractor

with date and seal.

Additional Conditions  with the contractor in cases where the cleaning and maintenance of sewerage system  is outsourced.

- The Contractor shall strictly abide by the directions of the Hon’ble High Court of Madras in its order dated 20.11.2008 in W.P.No. 24403/2008, and the orders of the Government of Tamilnadu in G.O.(MS) No. 293, M.A & W.S (MW) Department, dated 26.11.2010, regarding the ban on manual scavenging and on the entry  of sanitary workers into the sewerage system.  All cleaning and maintenance operations shall be done only through mechanical devices.

- The Contractor shall not allow sanitary workers to enter into the sewerage system for cleaning or maintenance operations except in the 4 circumstances permitted in the orders of the High Court in W.P.No. 24403, dated 20.11.2008 namely.

- For the removal of concrete/ FRP machine-hole door which gets damaged due to the heavy vehicular traffic and often falls inside the machine-hole causing obstructions/blocks in the sewer and which results in the blockage of sewerage system and where mechanical equipments cannot be put into operation.

- For the purpose of inter-linking the newly laid sewer main with the existing sewer main, where it will be wholly necessary too block the main sewer main in the servicing machine-hole.  Entry of sanitary workers on such occasions has to be necessarily permitted in as much as it is stated that large size sewer i.e., where the diameter is more than 300mm blocking the sewer main from the top of the machine-hole is not possible and only the sanitary worker has to enter the main hole and that too with necessary safety gadgets for blocking the sewer temporarily.

- For the removal of submersible pump sets fixed at the bottom of the suction wells, which goes out of order, for which the sanitary worker has to enter the well again with necessary safety gadgets after emptying the sewage from the well in order to remove the pump set.  It is made clear that before allowing any sanitary worker to enter on such occasions, steps should be taken to see that the sewage is totally emptied and thereby further ensure that no poisonous gas remains in the sewage line.

- For the reconstruction of the man hole of rectification of the sewer min due to any damage caused by sinking of man hole covers/sewer line when the sewage pipe line gets blocked or gets obstructed, which results in the system getting surcharged.  Here again, before allowing any sanitary worker to enter the sewer line, it is essential that sewage line is emptied by blocking the main holes in the system on either side of the sinking man holes/damaged man holes.

Even in the above four instances, the contractor should allow the workers to enter only with adequate safely gadgets and under the supervision of a qualified staff and only after duly observing all safety precautions including testing for the presence of toxic gases with a gas detector.  Naked flame method of testing the presence of poisonous gases is hazardous and should be strictly avoided.

- Even in the non-exceptional circumstances, consideration of safety of the workers shall be paramount and the contractor shall ensure the same.

- The Contractor should indemnify the employer for any loss or damage caused by his negligence or by his non-observance/violations of any labour laws.

- The contractor should take out insurance policies under the Workmen’s Compensation Act. 1923 for all the workers engaged by him and a photocopy of the insurance policy should be furnished to the employer.  The policy should be kept alive till completion of the contract.

- The Contractor should impart safety education to all his workers and train them in the use of safety gadgets.

- During the trial run period the sewer line are cleaned with Jet Roding machines only.

- The workmen engaged with safety gear and equipments only.

- The Contractor should be responsible to pay a compensation of US$ 0.016 Million or INR 1.00 Million in addition to the compensation paid by the State Government in the event of death due to asphyxiation have been identified of workmen in the Machine-hole for sewer line system while cleaning without safety gear and devices.